## icds_Work Item_20210829223058
ID | Title | Schedule | WorkitemType | PipelineType | RequestGroup | Size | Importance | ProgressStatus | Category | AssignedTo | ProjectManager | Project | Release | Theme | Chunk | Objectives | WorkItemPhase | PlanYear | PlanMonth | PlanQuarter | PlanWeek | ActualWeek | DueWeek | CompletedWeek | PlanDay | PlanDate | Session | PlanStartDate | PlanEndDate | ActualStartDate | ActualEndDate | PlanHours | ActualHours | SpentHours | C% | Top3 | Risk | Notes | HasImpediment | Executionsequence | UserAcceptance | ParentWorkItemID | AcceptanceCriteria | Description | StepsToReproduce | Resolution | BugCount | TargetCompletedPercentage | Flagged | Createdby | CreatedOn | BusinessUnit | Department
Bill_4_022 | VEndor - vendor notes - user icon/logo check VEndor - VEndor notes - workarea to be moved to top and details to bottom - check color VEndor - Vendor details - sections and grouping vendor list - redesign based on count | Immediate | Bug |  |  | Medium | B | In Progress |  | GovindaSamy R | Sankararam N | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Signoff | 2021 | M5 |  | W22 | W35 | [14 empty] | Medium | [12 empty] | Kiruthika Subramaninan | 06/01/2021 | CMS | Development
E1372 | In Vendor Balance report page >>The past due date not showing in red colour , refer image . | Immediate | Bug |  |  | Medium | B | New | Functional | GovindaSamy R | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/12/2021 | [6 empty] | Medium | Assigned to UI team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1222 | In Application >> The sorting option not in uniform in all pages , refer image for | A | Bug |  |  | Medium | B | In Progress | Functional | GovindaSamy R | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Testing | 2021 | M8 |  | W33 | W35 | W33 | W33 | D2 | 08/17/2021 |  | 08/17/2021 | 08/17/2021 | 08/17/2021 | 08/17/2021 | 0.5 | 0.5 | 0.5 | 100 |  | Medium | Bugs fixed and moved to QA | [11 empty] | Suresh vijayan | 07/20/2021 | Archarina | Development
E1426 | In Customer 360 page >> In Invoice tab >> The Bill status and due date , not showing color , refer image . | Immediate | Bug |  |  | Medium | B | New | Functional | GovindaSamy R | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/18/2021 | [6 empty] | Medium | Assigned to UI team | [11 empty] | Suresh vijayan | 08/18/2021 | Archarina | Development
E1448 | In Customer 360 details page >>KPI >>When user use lengthy email its showing outside of box, provide tooltip for email , refer image. | Immediate | Bug |  |  | Medium | B | New | Functional | GovindaSamy R | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/18/2021 | [6 empty] | Medium | Assigned to UI team | [11 empty] | Suresh vijayan | 08/18/2021 | Archarina | Development
E1482 | In Category list page >> We are getting server error message while uplaoding category file . In that validation , it showing GL account , refer image . | Immediate | Bug |  |  | Medium | B | New | Functional | GovindaSamy R | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to UI team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
E1413 | In Bill payment page >> In Filter >> The status drop down , all drop down values each word starting letter should be capital , refer image | A | Bug |  |  | Medium | B | In Progress | Functional | GovindaSamy R | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W33 | W35 | W33 | W33 | D2 | 08/17/2021 |  | 08/17/2021 | 08/17/2021 | 08/17/2021 | 08/17/2021 | 0.5 | 0.5 | 0.5 | 100 |  | Medium | Assigned to UI team | [11 empty] | Suresh vijayan | 08/16/2021 | Archarina | Development
E1414 | In Upload bills page >> When user enter total amount and click outside of the filed , page take time to load , refer vidoe -----F-----B | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/16/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/16/2021 | Archarina | Development
E1424 | In Customer 360 page >> In Notes tab >> Added notes timing showing wronglly , refer video | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/18/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/18/2021 | Archarina | Development
E1483 | In Category list page >> In GL iImport pop up >> We have validation column , but it not showing any validation . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
E1288 | In vendor list page >> When user import the vendor using existing email id , then the esisting email id vendor is deleted and deleted vendor detail are mapped to newly updated vendor , refer video | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | W35 | W34 | W34 | D2 |  |  |  |  | 08/02/2021 |  | 1 | 1 | 1 |  |  | Medium | Assigned Dev team | [11 empty] | Suresh vijayan | 07/29/2021 | Archarina | Development
E1293 | User having access to payment using offline option . In FM Login >> In Home/payment summary page Mark as paid option missing , but when user select pay now option , in payment details page we have mark as paid option , refer image . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W32 | W35 | W32 | W32 | D4 |  |  |  |  | 08/07/2021 |  | 1 | 1 | 1 |  |  | Medium | Assigned Dev team | [11 empty] | Suresh vijayan | 07/29/2021 | Archarina | Development
E1295 | In Vednor list page >> Download vendor option missing and in vvendor template , the contact number field accpeting more digit and it showing different format in app , refer image . Please confirm for the format . | Immediate | Bug |  |  | Medium | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 07/29/2021 | [6 empty] | Medium | Assigned PA team | [11 empty] | Suresh vijayan | 07/29/2021 | Archarina | Development
E1399 | In AP Aging Detailed report page >> Filter >> Provide Place holder for Date Filter , because its confusing for which date column ( Invoice or Due date ), refer image | Immediate | Bug |  |  | Medium | B | In Progress | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/12/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1455 | In Customer 360 page >> The contact tab >> The name should be contacts , refer image | Immediate | Improvement |  |  | Medium | B | In Progress | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/18/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/18/2021 | Archarina | Development
E1504 | In Clerk/Approver and FM home page >> The Split icon not showing , if the bill are splited , refer video . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/26/2021 | Archarina | Development
E1508 | In Application >> In Split pop up >> The Account name not showing , refer video . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/26/2021 | Archarina | Development
E1417 | In Add & Update Roles page >> Under ( Master ) , View Customer option is missing , Please confirm it should be display or what ? , refer image | Immediate | Improvement |  |  | Medium | B | In Progress | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/18/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/18/2021 | Archarina | Development
E1460 | In Unpaid bills report >> Due in Date and Over date data showing wrong , refer image. | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [7 empty] | D2 |  |  |  |  | 08/20/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/20/2021 | Archarina | Development
E1416 | In Payable preference page >> We are showing ' Configurations saved successfully ' for saving all data and as well Custom approval ( config conditions ) . Can we change Payable preference saved successfully for saving all data , refer video . | Immediate | Improvement |  |  | Medium | B | In Progress | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/16/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/16/2021 | Archarina | Development
E1445 | In Customer 360 details page >> tab name should be Bills or invoice, please confirm, refer image | Immediate | Improvement |  |  | Medium | B | In Progress | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/18/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/18/2021 | Archarina | Development
R1057 | In FM login >> For Flagged status >> We don't have flag option in action but when we click on any other option , in approvals page falg option is available , remove it . | Mid Term | Bug |  |  | Small | B | New | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  |  | 2021 | M3 | [10 empty] | 03/26/2021 | [6 empty] | Low | [12 empty] | Suresh vijayan | 03/26/2021 | Archarina | Development
E1056 | Mail not triggering when user submit the bill by using check box . | Immediate | Bug |  |  | Small | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 | [16 empty] | 04/23/2021 | [6 empty] | Medium | Assigned to developer " Charles Etti " | [11 empty] | Suresh vijayan | 04/23/2021 | Archarina | Development
Bill_4_007 | Dispute - placeholder is showing up as address.. appropriate placeholder to be given | Immediate | Bug |  |  | Medium | B | New |  | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Signoff | 2021 | M5 |  | W22 | W34 | [14 empty] | Medium | [12 empty] | Kiruthika Subramaninan | 06/01/2021 | Archarina | Development
E1101 | In All home page >> When user select any KPI/filter option , then the graph not showing like current finacial year after the paage load - Functional | Immediate | Bug |  |  | Small | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Testing | 2021 | M6 |  | W26 | W35 | W26 | W26 | D1 |  |  |  |  | 04/06/2021 |  | 1 | 1 | 1 |  |  | Medium | Assigned to testing team for test the bugs | [11 empty] | Suresh vijayan | 06/04/2021 | Archarina | Development
E1345 | In Unpaid bills report >>payment status column its showing only unpaid , but in filter payment status drop down we don't have unpaid option and please confirm filter payment status drop down values also because its showing "payment completed , payment faild and payment confirmation " values also, please confirm. | Immediate | Bug |  |  | Medium | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/04/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/04/2021 | Archarina | Development
E1346 | In Unpaid bills report>>filter>>approval status drop down >>rejected option need to show in approval status , Please confirm | Immediate | Bug |  |  | Medium | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/04/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/04/2021 | Archarina | Development
E1348 | In Unpaid Bills report page >> user exported file name showing as " Bill due based report" , please confirm . | Immediate | Bug |  |  | Medium | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/04/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/04/2021 | Archarina | Development
E1352 | In exported excel>> date are not showing in same format , refer image | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W33 | W35 | W33 | W33 | D4 |  |  |  |  | 08/04/2021 |  | 1 | 1 |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/04/2021 | Archarina | Development
E1354 | In Account payable preference >> custom approval>> user configured two condition and selected cancel option in payable preference page , but when user back to account payable preference page configured two conditions are showing | Immediate | Bug |  |  | Medium | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/04/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/04/2021 | Archarina | Development
E1365 | In Payable pereference page >> In Approval tab >> When user select auto approval radio option , then allow partial amount check box should be disable , refer image . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/12/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1371 | In Vendor Balance report page >> We have two vendor , if i have uploaded any bill under ine vendor . Then the total billable amount adding both the vendor amount , refer video | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | W35 | W34 | W34 | D2 |  |  |  |  | 08/12/2021 |  | 1 | 1 |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1383 | In Vendor balance report page >> The Next due in date showing wrongly , refer video . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis |  |  |  | W33 | [8 empty] | 08/12/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1394 | In AP Aging Summary report page >> Filter >> Total amount and Balance amount Filter not working , refer video | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/12/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1400 | In AP Aging Detailed report page >> Balance amount not showing in grid table date , refer image. | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | W35 | W34 | W34 | D2 |  |  |  |  | 08/12/2021 |  | 1 | 1 |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1403 | In AP Aging Detailed report page >> Disputed bill also showing in grid table date , refer image. | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | W35 | W34 | W34 | D2 |  |  |  |  | 08/12/2021 |  | 1 | 1 |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1408 | In AP Aging Detailed report page >> 91st due date bill amount not showing in grid table , refer image. | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis |  |  |  | W33 |  |  |  | D4 |  |  |  |  | 08/12/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/12/2021 | Archarina | Development
E1325 | In Bill Payments Report >> In Filter>> In grid header we using paid on date , but in filter its showing due date , refer image | Immediate | Improvement |  |  | Medium | B | In Progress | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 08/02/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/02/2021 | Archarina | Development
E1315 | In Payable preference page >> In Approval tab >> Custom approval table data , grid header sorting option missing and tool tip as well , refer image . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | W35 | W34 | W34 | D2 |  |  |  |  | 08/02/2021 |  | 1 | 1 |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/02/2021 | Archarina | Development
E1277 | FM Login>>Filter >> Vendor drop down >> empty name are showing | Immediate | Improvement |  |  | Medium | B | New | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [19 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 07/22/2021 | Archarina | Development
E1484 | In vendor balance report >> last payment date not showing in vendor balance report list page . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1486 | In Customer 360 page >> In Contact tab >> In updated contact >> last name automatically added in first name, after added or updated contact , refer video | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1488 | In Add/update customer page >> After removed attached company logo, when user select update option , server error message showing . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1489 | In Bills payment report >> filter >> paid by drop down >> all user name showing ( include other organization user name also ), refer image | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1490 | In AP Aging summary report >> Filter >> Balance amount filter not working for all condition , balance amount filter only fetching (0-30 days ) condition | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1491 | In Upload bills page >> When user created vendor , it not showing GL code , refer video . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1492 | In Vendor blc report page >> The Vendor having only one bill and his payment aslo completed , still Next Due in date showing the existing bill due date , refer video | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1493 | In Vendor blc report page >> Present date also showing in Overdue Bills amount , refer image . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/25/2021 | Archarina | Development
E1450 | In Customer 360 details page >> contact >> Sorting option not working and sorting symbol looks different , refer image. | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | W35 | W34 | W34 | D2 |  |  |  |  | 08/18/2021 |  | 1 | 1 |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/18/2021 | Archarina | Development
E1496 | In Payable perefrence page >> In Approval tab >> Choose Custom approval >> Select save without configure any custom approval , getting validation like 'Slect At Least One Approver | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/26/2021 | Archarina | Development
E1497 | In Customer list page >> Pagination missing . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/26/2021 | Archarina | Development
E1499 | In Clerk login >> For splited bills >> When user select split option under action >> The Account are not showing in split pop up , refer video | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/26/2021 | Archarina | Development
E1501 | In FM login >> Can we show the split icon at last icon under action instead of showing inbetween action , refer image | Immediate | Bug |  |  | Medium | B | In Progress | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W34 | [8 empty] | 08/25/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/26/2021 | Archarina | Development
E1465 | In Category list page >> Please provide Download category template option . | Immediate | Improvement |  |  | Medium | B | In Progress | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
E1470 | In Category list page >> If the user uploading file without adding discription , then the data are not populating in GL Import popup . The values are populating only when the discription value available , refer video . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
E1471 | In Category list page >> User unable to import the category , getting server error , refer video . | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
E1473 | In Category list page >> When user tried to upload invalid file , we are not getting validation message like invalid file choosed , refer video | Immediate | Bug |  |  | Medium | B | New | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
E1474 | In Category list page >> Select Browse option >> In GL import pop up >> Can we have sorting option , please confirm . | Immediate | Improvement |  |  | Medium | B | In Progress | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
E1481 | In Category import template >> Can we show Category GL Code instead of Category GL same for Sub category as well , bcos we are using Code in application . refer image | Immediate | Improvement |  |  | Medium | B | In Progress | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 | M8 |  | W34 | [8 empty] | 08/23/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 08/23/2021 | Archarina | Development
Bill_4_023 | vendor and mark as paid - payment mode dropdown - add cash | Immediate | Bug |  |  | Medium | B | New |  | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Signoff | 2021 | M5 |  | W22 | W34 | [14 empty] | Medium | [12 empty] | Kiruthika Subramaninan | 06/01/2021 | Archarina | Development
E1092 | While adding vendor from API , Kindly through error code when user without adding mandatory fields . | Immediate | Improvement |  |  | Small | B | New | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 | [16 empty] | 05/25/2021 | [6 empty] | Medium | Assigned to " Dev team " | [11 empty] | Suresh vijayan | 05/25/2021 | Archarina | Development
E1238 | In Vendor template >> Already existing email id accepting and when user use import vendor functionality then GL code is not showing in update vendor page , refer video . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Testing | 2021 | M17 |  | W29 | W35 | W29 | W29 | D5 | [6 empty] | 1 | 1 | 1 | 100 |  | Medium | Bugs fixed and assigned to QA | [11 empty] | Suresh vijayan | 07/21/2021 | Archarina | Development
E1225 | In Account payable reference page >> When user select cancel / save button , page navigating to Home page but , setting menu as been highlighted , refer video . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W32 | W35 | W32 | W32 | D4 | [6 empty] | 1 | 1 | 1 |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 07/21/2021 | Archarina | Development
E1253 | In Payable preference page >> approval tab >>user selected multi approver ( added two approver ) , but in bill upload page , selected approver name showing approver drop down , refer video . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Testing | 2021 | M17 |  | W29 | W35 | W29 | W29 | D5 | [6 empty] | 1 | 1 | 1 |  |  | Medium | Bugs fixed and assigned to QA | [11 empty] | Suresh vijayan | 07/21/2021 | Archarina | Development
E1246 | In Clerk login >> Already have few bills in awaiting approva status , when he got update permission for awaiting approval , then it will reflect for past bills ? please confirm . | Immediate | Improvement |  |  | Medium | B | In Progress | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [19 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 07/21/2021 | Archarina | Development
E1136 | In Customer list page >> user can able to delete Customer after mapped with Project also | Immediate | Bug |  |  | Small | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 06/15/2021 | [6 empty] | Medium | Assigned to " PA team " | [11 empty] | Suresh vijayan | 06/15/2021 | Archarina | Development
E1145 | In Customer list page >> in add customer option we have option like create , but in add customer page its showing " Add Customer " , please confirm its should be "Create or Add " to maintain the consistency , refer image . | Immediate | Bug |  |  | Small | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 06/15/2021 | [6 empty] | Medium | Assigned to " PA team " | [11 empty] | Suresh vijayan | 06/15/2021 | Archarina | Development
E1139 | In Customer create / update page >> Change Field and place holder for Email Id instead of Email | Immediate | Bug |  |  | Small | B | New | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 06/15/2021 | [6 empty] | Medium | Assigned to " PA team " | [11 empty] | Suresh vijayan | 06/15/2021 | Archarina | Development
E1146 | In Add Project page >> The Status field mentioned as optional , but it should be mandatory , Please confirm. | Immediate | Bug |  |  | Small | B | New | Clarification | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 06/15/2021 | [6 empty] | Medium | Assigned to " PA team " | [11 empty] | Suresh vijayan | 06/15/2021 | Archarina | Development
E1157 | In Upload bills page >> In Split amout pop up >> Provide hypen if description is not available , refer image . | Immediate | Bug |  |  | Small | B | New | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 06/21/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 06/21/2021 | Archarina | Development
E1199 | In Category list page >> Clear the empty records . | Immediate | Improvement |  |  | Medium | B | New | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 07/07/2021 | [6 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 07/07/2021 | Archarina | Development
E1262 | On Login page >> " Sign In "/ " Sign Up " and " Forgot Password " >> both words first letter showing in Capital letter. | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W32 | W35 | W32 | W32 | D4 | [6 empty] | 1 | 1 | 1 |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 07/22/2021 | Archarina | Development
E1280 | Roles >> He / She able to create and update roles without add permission | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W29 |  | W29 | W29 | D5 | [11 empty] | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 07/22/2021 | Archarina | Development
E1261 | On login page >> Session has expired validation message showing when a user copy and paste other than login page URL in Browser. | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W29 |  | W29 | W29 | D5 | [6 empty] | - |  |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 07/22/2021 | Archarina | Development
E1269 | FM>>Export bill >> export option not working initially , after filter data only export option working | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | 2021 |  |  | W29 |  | W29 | W29 | D5 | [6 empty] | - |  |  |  |  | Medium | Assigned to Dev team | [11 empty] | Suresh vijayan | 07/22/2021 | Archarina | Development
E1205 | In Approval login >> If any bill contained with multi approver , kindly show them as 1st Approver and 2nd Approver in settings tab , refer image . | Immediate | Improvement |  |  | Medium | B | New | Suggestion | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Analysis | [12 empty] | 07/20/2021 | [6 empty] | Medium | Assigned to PA team | [11 empty] | Suresh vijayan | 07/20/2021 | Archarina | Development
E1214 | In Admin login >> When admin set a permission only for user . In user login , he not having user permission , reer video . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Testing | 2021 | M17 |  | W29 | W29 | W29 | W29 | D5 |  |  |  |  | 07/29/2021 |  | 1 | 1 | 1 |  |  | Medium | Comments provided for the bugs and assigned to QA | [11 empty] | Suresh vijayan | 07/20/2021 | Archarina | Development
E1218 | In Client admin login >> When user select delete option for pending status client , client status changed to Disabled status and user able change status to active by using Activation option . | Immediate | Bug |  |  | Medium | B | In Progress | Functional | Sankararam N | Priya P | ArcBill | ARC-BIL-2021M8V11.2 |  |  |  | Testing | 2021 | M17 |  | W29 | W29 | W29 | W29 | D5 |  |  |  |  | 08/02/2021 |  | 1 | 1 | 1 |  |  | Medium | Comments provided for the bugs and assigned to QA | [11 empty] | Suresh vijayan | 07/20/2021 | CMS | Development